Newcastle City Council

Air Quality Action Plan

In fulfilment of Part IV of the Environment Act 1995, as amended by the Environment Act 2021

Local Air Quality Management

2026 to 2030

| Information | Newcastle City Council Details |
| --- | --- |
| Local Authority Officer | Environmental Protection |
| Department | Public Safety and Regulation |
| Address | Newcastle City Council, 7th Floor, Civic Centre, Newcastle upon Tyne NE1 8QH |
| Telephone | 0191 2116102 |
| E-mail | psr@newcastle.gov.uk |
| Report Reference Number | NCC AQAP 2026 to 2030 |
| Date | February 2026 |

# Executive Summary

This Air Quality Action Plan (AQAP) has been produced as part of our statutory duties required by the Local Air Quality Management framework. It outlines the actions we will take to improve air quality in Newcastle City Council between 2026 and 2030. The AQAP sets out how the local authority will exercise its functions in order to secure the achievement of the air quality objectives.

This action plan is a draft version and will be adopted from [TBC]. Implementation of the outlined measures will result in the relevant objective(s) being attained by 2026.

The relevant Air Quality Management Areas (AQMAs) addressed by this action plan are outlined below:

- AQMA No. 1b (city centre) which was declared in 2008 for exceedances of the annual mean objective for nitrogen dioxide (NO2).

It is the intention of Newcastle City Council to revoke AQMA No. 5 (Gosforth) as annual mean NO2 concentrations have been compliant for five years.

This action plan replaces the previous action plan which ran from 2006 – 2025. Projects delivered through the past action plan include:

- Enabling people to choose active travel and public transport;

- Implementation of the Clean Air Zone (CAZ) to improve emissions from road transport;

- Encouraging the correct use of solid fuel appliances;

- Decriminalising parking enforcement;

- Enforcing idling engines legislation;

- Car Loan Schemes;

- Use of car parking charges to encourage alternatives;

- Electric by default policy, meaning consideration must be given to procuring electric vehicles prior to petrol or diesel and a case made for anything other than electric;

- Switch EV Council Trial;

- Switch EV Public Trial; and

- Switch EV Car Club Trial.

Air pollution is associated with a number of adverse health impacts. It is recognised as a contributing factor in the onset of heart disease and cancer. Additionally, air pollution particularly affects the most vulnerable in society: children and older people, and those with heart and lung conditions. There is also often a strong correlation with equalities issues because areas with poor air quality are also often less affluent,.

The UK Health Security Agency (formally Public Health England) has estimated that the costs of air pollution in England to health and social care services could reach between £5.3 and 18.6 billion between 2018 and 2035 . Newcastle City Council is committed to reducing the exposure of people in Newcastle to poor air quality in order to improve health.

We have developed actions that can be considered under five broad topics:

- Alternatives to private vehicle use;

- Policy guidance and development control;

- Promoting low emission transport;

- Promoting travel alternatives; and

- Vehicle fleet efficiency.

Our priorities are to achieve compliance with the NO2 annual mean objective within the AQMA and maintain compliance for at least three years to enable revocation of the AQMA, to achieve compliance with the NO2 annual mean Limit Values within the CAZ and work towards revocation of the CAZ, and to collaborate with North East Combined Authority (NECA) on transport related issues, including the electrification of buses, as bus emissions have been identified as the primary contributor to remaining exceedances of the NO2 annual mean objective.

In this AQAP, we outline how we plan to effectively tackle air quality issues within our control. This AQAP is aligned with the Council Plan 2024 – 2027 which serves as the foundation of the Council’s delivery framework. The Plan sets out three interconnected overarching priorities: inclusive economy, anti-poverty, and net zero. The AQAP indirectly supports the net zero priority by addressing air pollution.   However, we recognise that there are a large number of air quality policy areas that are outside of our influence (such as vehicle emissions standards) but for which we may have useful evidence, and so we will continue to work with regional and central government on policies and issues beyond Newcastle City Council’s direct influence.

## Responsibilities and Commitment

This AQAP was prepared by AECOM on behalf of the Environmental Health Department of NCC with the support and agreement of the following officers and departments:

Environment Team, Public Safety and Regulation

This AQAP has been approved by:

To be completed once consultation complete.

The following Air Quality Partners / stakeholders have contributed to the development of the AQAP and will be committed to delivery of actions:

- Newcastle City Council Public Safety and Regulation;

- North East Combined Authority (NECA);

- Newcastle City Council Transport Planning;

- Newcastle City Council City Transport;

- Newcastle City Council Policy; and

- Newcastle City Council Capital Investment and Growth.

This AQAP will be subject to an annual review, appraisal of progress and reporting to the relevant Council Committee. Progress each year will be reported in the Annual Status Reports (ASRs) produced by Newcastle City Council as part of our statutory Local Air Quality Management duties.

If you have any comments on this AQAP please send them to Let’s Talk Newcastle.

Table of Contents

Executive Summary	i

Responsibilities and Commitment	iii

1	Introduction	1

2	Summary of Current Air Quality in Newcastle City Council	2

2.1	Air Quality Management Areas	2

2.2	Clean Air Zone	4

2.3	Public Exposure	4

3	Newcastle City Council’s Air Quality Priorities	10

3.1	Public Health Context	10

3.2	Planning and Policy Context	11

3.3	Source Apportionment	13

3.3.1	Automatic Number Plate Recognition Analysis	13

3.3.2	Road Traffic Data Source Apportionment NO2	17

3.3.3	Road Traffic Data Source Apportionment PM10 and PM2.5	21

3.4	Required Reduction in Emissions	25

3.4.1	Required Reduction	25

3.4.2	Future Baselining	26

3.5	Key Priorities	30

4	Development and Implementation of Newcastle City Council AQAP	31

4.1	Consultation and Stakeholder Engagement	31

4.2	Steering Group	32

5	AQAP Measures	33

5.1	Cost Benefit Analysis	33

5.2	Timescales of the AQAP Measures	40

5.3	Air Quality Partners	40

5.4	Maintaining Safe Air Quality	40

6	Quantification of Measures	41

6.1	Measure 1 – Clean Air Zone	41

6.2	Measure 2 – Electrifying the bus fleet	44

6.3	Measure 3 – Exposure Limitation at Stephenson Road	47

6.4	Measure 6 – Car Clubs	48

6.5	Measure 8 – Electric charging infrastructure	49

6.6	Overall Quantification	49

Appendix A: Response to Consultation	50

Appendix B: Reasons for Not Pursuing Action Plan Measures	51

Appendix C: Planning and Policy Detail	53

C.1 National Planning and Policy Context	53

C.2 Regional Planning and Policy Context	57

C.3 Local Planning and Policy Context	62

Glossary of Terms	68

List of Tables

Table 2.1 – Relevant Declared Air Quality Management Areas	3

Table 2.2 – Monitoring Locations that Exceeded the Air Quality Objective (or were within 10% of exceeding) in 2024	5

Table 2.3 – Estimated annual mean NO2 concentrations at relevant exposure of the exceeding sites and sites within 10% of the air quality objective	7

Table 3.1 – Summary of Relevant Policy	11

Table 3.2 – Required NOx emission reduction at the worst-case receptor location in AQMA 1b (Market Street (DT8))	25

Table 3.3 – Local Traffic Growth Factors from TEMPro	26

Table 3.4 – Projected NOx Emissions for Market Street	27

Table 3.5 – Predicted reductions in annual mean NO2 concentrations at Market Street	28

Table 4.1 ‒ Consultation Undertaken	31

Table 5.1 ‒ Cost Benefit Analysis of short-listed actions	34

Table 5.2 ‒ Air Quality Action Plan Measures	36

Table 6.1 ‒ Modelled annual mean NO2 concentrations for PCM link 47526 in 2023	42

Table 6.2 ‒ Average daily buses going through Market Street and St Mary’s Place that are part of the bus electrification plans	45

Table 6.3 ‒ Proportions of buses to be electrified in 2026	45

Table 6.4 ‒ Predicted annual mean NO2 concentrations at Market Street and St Mary’s Place with and without the bus electrification in 2026	46

Table 6.5 – Non-automatic NO2 Fall off With Distance Calculations (concentrations presented in µg/m3)	47

Table 6.6 – Annual NOx emissions savings from one Euro 6 Car Club car replacing 15 privately owned vehicles	48

Table 6.7 – Calculation of total mileage travelled daily by an Electric Vehicle (EV) charged at a ultra rapid charger of 50kWh +	49

List of Figures

Figure 2.1- Air Quality Management Area and Clean Air Zone	4

Figure 2.2 - Monitoring locations that exceeded the Air Quality Objective (or were within 10% of exceeding) in 2024	6

Figure 2.3 - Annual Mean NO2 Concentration Trends at all Monitoring Sites in Newcastle 2019 – 2024	8

Figure 2.4 - Annual Mean PM10 Concentration Trends at all Monitoring Sites in Newcastle 2020 – 2024	9

Figure 2.5 - Annual Mean PM2.5 Concentration Trends at all Monitoring Sites in Newcastle 2020 – 2024	10

Figure 3.1 - Car Euro Classification, ANPR and EFT v13.1, 2024	15

Figure 3.2 - LGV, HGV and Bus Euro Classification, ANPR and EFT v13.1, 2024	16

Figure 3.3 - Total NO2 Source Apportionment at Market Street (DT8)	17

Figure 3.4 - NO2 Source Apportionment at Market Street (DT8) – Background Contribution Detail	18

Figure 3.5 - Total NO2 Source Apportionment at St Mary’s Place (DT5/115/116)	19

Figure 3.6 - NO2 Source Apportionment at St Mary’s Place (DT5/115/116) – Background Contribution Detail	19

Figure 3.7 - Total NO2 Source Apportionment at Stephenson Road (DT81)	20

Figure 3.8 - NO2 Source Apportionment at Stephenson Road (DT81) – Background Contribution Detail	21

Figure 3.9 - Total PM10 Source Apportionment at Jesmond Road (Cradlewell continuous monitor)	22

Figure 3.10 - PM10 Source Apportionment at Jesmond Road (Cradlewell continuous monitor) – Background Contribution Detail	23

Figure 3.11 - PM10 Source Apportionment at St Mary’s Place (Newcastle City Centre continuous monitor) – Background Contribution Detail	24

Figure 3.12 - PM2.5 Source Apportionment at St Mary’s Place (Newcastle City Centre continuous monitor) – Background Contribution Detail	24

Figure 3.13 - Percentage change of emissions based on 2024 at Market Street	28

Figure 6.1 - Proportion of compliant and non-compliant vehicles entering the Clean Air Zone in 2024	43

Figure 6.2 - Projected proportion of compliant and non-compliant Diesel Cars, Diesel LGVs and Buses entering the Clean Air Zone from 2025 – 2030	44

# Introduction

This report outlines the actions that Newcastle City Council will deliver between 2026 - 2030 in order to reduce concentrations of air pollutants and exposure to air pollution; thereby positively impacting on the health and quality of life of residents and visitors to the Newcastle City Council administrative area. The purpose of the report is to set out how the local authority will exercise its functions in order to achieve the relevant air quality objectives. This action plan is a draft version and will be adopted from [TBC].

It has been developed in recognition of the legal requirement on the local authority to achieve and maintain Air Quality Objectives under Part IV of the Environment Act 1995, as amended by the Environment Act 2021, and to meet the requirements of the Local Air Quality Management (LAQM) statutory process.

This Plan will be reviewed every five years at the latest and progress on measures set out within this Plan will be reported on annually within Newcastle City Council’s air quality Annual Status Report (ASR).

# Summary of Current Air Quality in Newcastle City Council

## Air Quality Management Areas

The relevant Air Quality Management Areas (AQMAs) addressed by this AQAP are outlined below.

Two AQMAs have been declared by Newcastle City Council for exceedances of the annual mean objective for nitrogen dioxide (NO2) in 2008. AQMA No. 1b (city centre) encompasses the previous AQMAs 1-3, covering Newcastle city centre. AQMA No. 5 (Gosforth) encompasses parts of the A189 and B1318 in Gosforth.

It is the intention of Newcastle City Council to revoke AQMA No. 5 (Gosforth) as annual mean NO2 concentrations have been compliant for five years.

This AQAP therefore covers AQMA No. 1b (city centre) only. The extent of AQMA No. 1b can be seen in Figure 2.1.

Table 2.1 – Relevant Declared Air Quality Management Areas

| AQMA Name | Date of Declaration | Pollutants and Air Quality Objectives | One Line Description | Is air quality within the AQMA influenced by National Highways roads? | Level of Exceedance: Declaration | Level of Exceedance: Current Year | Number of Years Compliant with Air Quality Objective |
| --- | --- | --- | --- | --- | --- | --- | --- |
| AQMA No. 1b (city centre) | Declared April 2008 | NO2 Annual Mean | An area encompassing the previous AQMAs 1-3, covering Newcastle city centre. | No | 127.3 µg/m3 (measured 2004 concentration) | 38.5 | 0 years |

## Clean Air Zone

In January 2023, a Government mandated Clean Air Zone (CAZ) was implemented in part of Newcastle and Gateshead. This CAZ is a class C that charges all buses, coaches, taxis, private hire vehicles (PHVs), heavy goods vehicles (HGVs), vans and minibuses that do not meet the Euro 6/VI emissions standards for diesel vehicles and Euro 4 for petrol vehicles. The extent of the CAZ can be seen in Figure 2.1.

Figure 2.1- Air Quality Management Area and Clean Air Zone

## Public Exposure

Newcastle has an estimated population of 300,200 (in 2021). Approximately 45,361 people (in mid-2022) are living within the AQMA No. 1b (city centre), however, not all are exposed to nitrogen dioxide (NO2) in exceedance of the air quality objective. Newcastle is an urban area and its road network features major arterial roads including the A1 which runs from north to south through the Council’s administrative area, the A167(M) which connects the city and the Tyne Bridge to the A1, and the A1058 which connects the city to the coast. A summary of the current air quality (2024) in the Council’s administrative area is provided below.

Newcastle operates a monitoring network comprising of four automatic monitoring analysers (continuous ambient monitoring sites (CMS)), monitoring NO2, particulate matter (PM10 and PM2.5) and ozone (O3) as well as 62 NO2 passive diffusion tube monitoring sites.

In 2024, there were two monitoring locations which monitored NO2 concentrations above the annual mean objective for NO2 of 40 µg/m3, and another three monitoring locations within 10% of the annual mean objective for NO2. Details of these sites are provided in Table 2.2 below and they are shown in Figure 2.2.

Table 2.2 – Monitoring Locations that Exceeded the Air Quality Objective (or were within 10% of exceeding) in 2024

| Location | ID | X | Y | Annual mean NO2 concentration (µg/m3) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 2020 | 2021 | 2022 | 2023 | 2024 |
| 10 Market Street | DT8 | 424936 | 564333 | 29.8 | 39.9 | 44.7 | 42.2 | 38.5 |
| John Dobson Street | DT102 | 425106 | 564466 | 23.4 | 32.5 | 45.1 | 33.1 | 36.4 |
| St Mary’s Place | DT5, DT115, DT116 | 424948 | 564872 | 37.5 | 44.2 | 46.3 | 40.3 | 36.3 |
| Stephenson Road, entrance to Jesmond Pk West | DT81 | 426546 | 566260 | 56.8 | 97.7 | 92.2 | 67.1 | 64.5 |
| Percy Street | Percy Street CMS | 424776 | 564861 | 39.0 | 42.0 | 43.0 | 42.4 | 41.1 |
|  | DT29, DT30, DT31 |  |  | 39.5 | 50.8 | 53.3 | 45.9 | 44.0 |
| Bold text denotes exceedance of annual mean objective Bold and underlined text denotes NO2 annual means exceeding 60 µg/m3, indicating a potential exceedance of the 1-hour mean objective |  |  |  |  |  |  |  |  |

Figure 2.2 - Monitoring locations that exceeded the Air Quality Objective (or were within 10% of exceeding) in 2024

DT8 is situated on a road with several bus stops, where idling bus engines likely contribute to higher pollutant levels. DT102 (John Dobson Street) is positioned on a road with heavy bus traffic and traffic associated with the recent redevelopment of East Pilgrim Street, leading to elevated concentrations. The triplicate site DT5, DT115, and DT116 is near pedestrian-controlled traffic lights and a bus stop, where frequent braking and acceleration increase pollutant levels. The triplicate site DT29, DT30, and DT31 is co-located with the automatic monitor on Percy Street, which experiences high bus traffic due to its proximity to the bus station, contributing to elevated concentrations. DT81 is located by a dual carriageway on an incline that often faces congestion, leading to higher pollutant levels.

However, many of these sites are not at relevant exposure, for example, residential accommodation, as they are located at roadside locations, so they require distance correction. The annual mean NO2 concentrations at relevant exposure following distance correction are listed in Table 2.3. DT102 is not representative of relevant exposure and has therefore been excluded from the assessment. DT8 and DT5/115/116 did not require distance correction as they are already located at relevant exposure but are replicated here for a complete dataset.

Table 2.3 – Estimated annual mean NO2 concentrations at relevant exposure of the exceeding sites and sites within 10% of the air quality objective

| Location | ID | X | Y | Annual mean NO2 concentration (µg/m3) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 2020 | 2021 | 2022 | 2023 | 2024 |
| 10 Market Street | DT8 | 424936 | 564333 | 29.8 | 39.9 | 44.7 | 42.2 | 38.5 |
| St Mary’s Place | DT5, DT115, DT116 | 424948 | 564872 | 37.5 | 44.2 | 46.3 | 40.3 | 36.3 |
| Stephenson Road, entrance to Jesmond Pk West | DT81 | 426546 | 566260 | 34.8 | 52.3 | 48.9 | 37.6 | 35.8 |
| Percy Street | Percy Street CMS | 424776 | 564861 | 34.2 | 36.5 | 37.1 | 36.5 | 34.7 |
|  | DT29, DT30, DT31 |  |  | 34.6 | 43.1 | 44.8 | 39.1 | 33.0 |
| Bold text denotes exceedance of annual mean objective |  |  |  |  |  |  |  |  |

Therefore, the remaining sites that are within 10% of the annual mean objective (>36 µg/m3 and <40 µg/m3) or above annual mean objective (>40 µg/m3) in 2024 are listed below:

- DT8 (10 Market Street) with 38.5 µg/m3

- Triplicate site DT5, DT115 and DT116 (St Mary’s Place) with 36.3 µg/m3

As stated above, the elevated concentrations at both these sites are closely associated with bus emissions.

Due to the uncertainty inherent in diffusion tube monitoring methods, concentrations within 10% of the annual mean objective are not considered compliant for LAQM purposes, therefore, Newcastle was not considered to be compliant with the annual mean objective for NO2 in 2024.

From 2019 to 2024, Newcastle followed the UK downward trend in annual mean NO2 concentrations for urban background and roadside sites, with an average reduction of 46.4% and 43.1%, respectively, as shown in Figure 2.3.

Figure 2.3 - Annual Mean NO2 Concentration Trends at all Monitoring Sites in Newcastle 2019 – 2024

Since 2019, all 64 monitoring locations in Newcastle have followed the UK trend and have observed decreases in annual mean NO2 concentrations at urban background and roadside sites. The biggest average decrease of 60.6% was observed at DT25, DT127, DT128 (located at Strawberry Place within AQMA 1b (city centre)). The lowest average decrease of 20.8% was observed at the automatic monitor at Percy Street.

Overall, it seems that there was a significant reduction in NO2 concentrations when the Covid-19 restrictions were in place in 2020. Since then, NO2 concentrations have increased from these low concentrations, but have not returned to pre-pandemic concentrations. The introduction of the CAZ in 2023 has also likely contributed to decreases in pollutant concentrations.

Within the AQMA No. 1b (city centre), the monitored PM10 concentrations at two automatic monitors range from 10.7 µg/m3 to 16.2 µg/m3 from 2019 – 2024, as shown in Figure 2.4. This is well below the annual mean PM10 objective of 40 µg/m3. Similarly, the monitored PM2.5 concentrations range from 5.5 µg/m3 to 7.4 µg/m3 across the same time period, as shown in Figure 2.5. These concentrations are also below the annual mean PM2.5 target value of 10 µg/m3 by 2040. However, it is widely recognised that there is no safe level of particulate pollution and health impacts are expected even below these values.

Figure 2.4 - Annual Mean PM10 Concentration Trends at all Monitoring Sites in Newcastle 2020 – 2024

Figure 2.5 - Annual Mean PM2.5 Concentration Trends at all Monitoring Sites in Newcastle 2020 – 2024

Overall, from 2019 to 2024, Newcastle followed the UK downward trend in annual mean PM10 concentrations, with an average reduction of 16.4% at the urban background monitor Newcastle Centre AURN and 19.8% at the urban roadside monitor Cradlewell AURN, as shown in Figure 2.4. While monitored urban background PM10 concentrations are generally slightly elevated compared to the UK urban background mean except for in year 2022 and 2023, the recorded urban roadside PM10 concentrations have tracked below the average UK urban roadside PM10 concentrations from 2020 – 2024.

Overall, from 2019 to 2024, Newcastle followed the UK downward trend in annual mean PM2.5 concentrations, with an average decrease of 2.7%, as shown in Figure 2.5. Furthermore, PM2.5 concentrations in Newcastle tracked below the average UK urban background PM2.5 concentrations at the urban background monitor Newcastle Centre AURN from 2019 – 2023, and in 2024 the monitored PM2.5 concentrations are only slightly elevated compared to the UK urban background mean.

# Newcastle City Council’s Air Quality Priorities

## Public Health Context

Air pollution is the largest environmental risk to public health in the UK and can cause and worsen health conditions, particularly in the most vulnerable groups of society including children, the elderly, individuals with existing cardiovascular or respiratory diseases, pregnant women and low-income communities.

The Public Health Outcomes Framework includes PM2.5 as a key indicator of mortality, this is the mortality burden associated with long term exposure to particulate matter and is expressed as a percentage of annual deaths from all causes in the population over 30 years of age. The fraction of mortality attributable to particulate air pollution in Newcastle in 2023 was 5.0%. This is slightly lower than the average for English local authorities of 5.2%. However, it is higher than the average of the North East region of 4.6%.

## Planning and Policy Context

The air quality action plan exists within a comprehensive network of planning and policy documents on a local, regional, and national scale, which work together to contribute towards improvements in air quality in Newcastle.

A list of relevant policy is provided in Table 3.1 below, considering air quality specific policy, planning policy, transport policy (which has a key impact on air quality due to the sector’s contribution to emissions), and climate policy (which often has co-benefits for air quality as actions to reduce CO2 emissions also reduce NO2 and PM emissions).

Table 3.1 – Summary of Relevant Policy

| Topic | Local Policy | Regional Policy | National Policy |
| --- | --- | --- | --- |
| Air Quality | Newcastle AQAP (this document); Smoke Control Area and Solid Fuel Enforcement Policy |  | Environment Act 2021; Clean Air Strategy (2019); Air Quality Strategy (2023) |
| Planning | Newcastle Local Plan; Health and Wellbeing Strategy 2023 - 2028 | The Interim North East Local Growth Plan 2025 | National Planning Policy Framework (2024) |
| Transport | Emerging Newcastle Movement Strategy; Newcastle Green Infrastructure Strategy | North East Local Transport Plan; Go Ultra Low North East; North East Active Travel Strategy 2023; Making the Right Travel Choice Strategy 2022; Bus Service Improvement Plan 2023 Zero Emission Vehicle Strategy 2023 Rail and Metro Strategy | Emerging Integrated National Transport Strategy |
| Climate | Net Zero Newcastle 2030 action plan Council Plan 2024 - 2027 |  | Net Zero Strategy: Build Back Greener (2021) |

All policies listed in Table 3.1 are described in detail in Appendix C. Items of specific note are:

- Work has started on preparation of a joint Local Plan working with Gateshead Council. Central government is keen to bring forward partnership working between Local Planning Authorities and Combined Authorities. The current Local Plan is a collection of documents that guides future development in Newcastle to 2030 which consist of two parts: the Core Strategy and Urban Core Plan (CSUCP), and the Development and Allocation Plan (DAP). The CSUCP 2010 - 2030 is a strategic planning framework that guides development in Newcastle and Gateshead to 2030. Air Quality is discussed under policy CS14 Wellbeing and Health. The DAP 2015 - 2030  provides more detailed policies to support growth ambitions for Newcastle. Air Quality is discussed under policy DM24 Environmental and Health Impacts of Development and DM32 Minerals Extraction and Reclamation. These planning policies support the aims of the AQAP.

- The Newcastle Movement Strategy is currently emerging, and will supplement the North East Transport Plan, the North East Combined Authority’s core strategy for transport, which sets out the regional ambitions up to 2040 as well as Newcastle and Gateshead’s Local Plan, which sets out how wider development and planning policy will help to shape the city in the coming years. The Movement Strategy will guide transport development until 2045, creating a transport network that is efficient, safe, accessible and inclusive. One focus point is to improve the wider environment by reducing Newcastle’s carbon footprint. Therefore, this policy supports the aims of the AQAP in the transport space.

- The Net Zero Newcastle 2030 action plan presents Newcastle’s view of how the city can achieve its ambition to be Net Zero carbon by 2030. The primary priority for Net Zero Newcastle is to focus on the immediate improvement to air quality that can be achieved by addressing harmful emissions by reducing the dominance of the private car on the city and facilitating a dramatic growth in active travel. The Priority Action T3 refers indirectly to air quality. Therefore, this policy supports the aims of the AQAP in the climate space.

## Source Apportionment

The AQAP measures presented in this report are intended to be targeted towards the predominant sources of emissions within Newcastle City Council’s area.

A source apportionment exercise was carried out by Newcastle City Council in 2025.

NO2 source apportionment was carried out following LAQM.TG(22) guidance at the two non-compliant locations, Market Street (DT8) and St Mary’s Place (DT5, DT115, DT116) using traffic count data for those roads for 2024 and ANPR fleet analysis data, alongside background pollutant concentration data from DEFRA. Only those two sites were considered as they exceeded the air quality objective for annual mean NO2 in 2024. Furthermore, Stephenson Road (DT81) was also considered as recorded annual mean NO2 concentration indicates a potential exceedance of the hourly mean NO2 exceedance.

PM2.5 and PM10 source apportionment has also been carried out at the Cradlewell and Newcastle Centre CMS sites where data is available.

Full details on the source apportionment exercise and its outcomes are summarised below.

### Automatic Number Plate Recognition Analysis

An Automatic Number Plate Recognition (ANPR) survey was undertaken on Market Street, St Mary’s Place and Stephenson Road in July 2024, which has informed this AQAP. These data were used to determine fleet breakdown by Euro classification. The Euro classification is based on the vehicle age and reflect compliance with increasingly stringent emissions standards in newer vehicles and is therefore directly related to the emissions produced by the fleet.

Where the ANPR records did not include counts of specific vehicles, such as taxis, hybrid buses and conventional/hybrid coaches, then the Euro classification for these vehicle types was based on the default data in DEFRA’s Emissions Factors Toolkit (EFT) v13.1, which is the standard tool for emissions modelling in the UK.

The 2024 ANPR fleet is compared to the default EFT v13.1 fleet in Figure 3.1and Figure 3.2 below. It can be seen that overall, the Newcastle petrol car fleet is similar to the national fleet. Newcastle has slightly more Euro 4 petrol cars with 10.9% compared to the national fleet with 9.5%. For diesel cars it can be seen that the Newcastle fleet is ahead of the national fleet in regard to Euro 6 with 65.3% and 55.0%, respectively.

Similarly, LGVs and rigid HGVs are slightly newer than the national fleet, with 76.2% of diesel LGVs being Euro 6 (against a national 74.9%) and 92.8% of rigid HGVs (against a national 86.9%). This may be as a result of the CAZ. The articulated fleet is more consistent with the national distribution, which may be expected as these tend to operate over larger distances and on the strategic road network.

The local bus fleet is expected to differ from the national fleet published in the EFT as it will be subject to unique commercial operating constraints. However, when compared to the EFT it is clear that the local fleet recorded in the counts is slightly lagging behind the national fleet due to a higher proportion being Euro V with 44.2% (against a national 18.7%). Buses are a key priority area for this AQAP as both remaining exceeding locations are on busy bus routes/close to bus stops.

Figure 3.1 - Car Euro Classification, ANPR and EFT v13.1, 2024

Figure 3.2 - LGV, HGV and Bus Euro Classification, ANPR and EFT v13.1, 2024

### Road Traffic Data Source Apportionment NO2

Analysis of emissions at DT8 Market Street, DT5/115/116 St Mary’s Place and DT81 Stephenson Road has been undertaken using the EFT v13.1 and local fleet data for 2024 to determine the main vehicle contributions of NO2.

Market Street

Figure 3.3 shows that the direct road contribution accounts for 58% (22.4 µg/m3) of total average NO2 with buses representing the largest proportion with 50% (19.2 µg/m3), followed by diesel cars with 5% (1.8 µg/m3) of total NO2 measured concentration at Market Street. Regional background, NO2 transported into an area by the wind from further away, accounts for 15% (5.7 µg/m3) while local background accounts for 27% (10.4 µg/m3) of total NO2.

Figure 3.3 - Total NO2 Source Apportionment at Market Street (DT8)

Based on the DEFRA background maps, the background contributions at Market Street are dominated by road emissions (36%) with a substantial contribution from other emissions (30%) as shown in Figure 3.4.

Figure 3.4 - NO2 Source Apportionment at Market Street (DT8) – Background Contribution Detail

St Mary’s Place

Figure 3.5 shows that direct road contribution accounts for 55% (20.2 µg/m3) of total average NO2 with buses and diesel cars representing the largest proportions, 42% (15.4 µg/m3) and 8% (3.1 µg/m3) of total NO2 measured concentration respectively, at St Mary’s Place. Regional background accounts for 16% (5.7 µg/m3) while local background accounts for 29% (10.4 µg/m3) of total NO2.

Figure 3.5 - Total NO2 Source Apportionment at St Mary’s Place (DT5/115/116)

Based on the DEFRA background maps, the background contributions at St Mary’s Place are dominated by road emissions (36%) with a substantial contribution from other emissions (30%) as shown in Figure 3.6.

Figure 3.6 - NO2 Source Apportionment at St Mary’s Place (DT5/115/116) – Background Contribution Detail

The local bus fleet plays a significant role in the air quality at Market Street and St Mary’s Place in relation to NO2 emissions. Analysis shows that direct road traffic contributes 58% and 55% of the total average NO2 with buses alone accounting for 50% and 42% of the total NO2 measured concentration at Market Street and St Mary’s Place, respectively (as shown in Figure 3.3 and Figure 3.5). This high impact is explained by the busy bus routes that pass these monitoring locations, along with the composition of the local bus fleet which differs from the national average. While the national fleet includes a higher proportion of newer, cleaner vehicles, the local fleet is lagging behind, with 44.2% of buses still classified as Euro V, compared to just 18.7% nationally (as shown in Figure 3.2). This indicates a slower transition to Euro VI or zero-emission buses locally which directly correlates with the elevated NO2 levels observed. Addressing this disparity by accelerating the upgrade of the local bus fleet would therefore be a critical step in reducing NO2 concentrations.

Stephenson Road

Figure 3.7 shows that the direct road contribution accounts for 80% (51.4 µg/m3) of total average NO2 with diesel cars and LGVs representing the largest proportions, 39% (25.2 µg/m3) and 24% (15.5 µg/m3) of total NO2 measured concentration respectively, at Stephenson Road. Regional background accounts for 9% (5.7 µg/m3) while local background accounts for 11% (7.4 µg/m3) of total NO2.

Figure 3.7 - Total NO2 Source Apportionment at Stephenson Road (DT81)

Based on the DEFRA background maps, the background contributions at Stephenson Road are dominated by road emissions (44%) with a substantial contribution from domestic emissions (19%) which are NO2 emissions from domestic, institutional and commercial space heating, as shown in Figure 3.8.

Figure 3.8 - NO2 Source Apportionment at Stephenson Road (DT81) – Background Contribution Detail

In summary, this indicates that actions targeted towards reducing emissions from road vehicles, particularly buses at Market Street and St Mary’s Place, and diesel cars at Stephenson Road, are likely to be most effective to reducing NO2 emissions concentrations in Newcastle upon Tyne.

### Road Traffic Data Source Apportionment PM10 and PM2.5

Analysis of emissions at the Cradlewell CMS on Jesmond Road and at the Newcastle Centre CMS has been undertaken using the EFT v13.1 and ANPR data for St Mary’s Place and DfT data for Jesmond Road for 2024 to determine the main source contributions of PM10 and PM2.5. It was decided to use the DfT data for Jesmond Road instead of the ANPR data for Stephenson Road which is located further north-east as the DfT counter is located closer to the Cradlewell CMS and therefore represents the traffic breakdown better.

Jesmond Road

Figure 3.9 shows that direct road contributions account for only 4% (0.5 µg/m3) of total PM10 concentration at Jesmond Road. Background pollution accounts for the majority 96% (12.5 µg/m3) of total PM10.

Figure 3.9 - Total PM10 Source Apportionment at Jesmond Road (Cradlewell continuous monitor)

Figure 3.10 shows the breakdown of PM10 background contributions at Jesmond Road from DEFRA background maps. 61% of background PM10 concentrations at Jesmond Road are categorised as “Other”. Of the three defined sources, road traffic contributes only 9% of background PM10 and PM2.5 concentrations at both locations. This indicates that PM10 is much less influenced by road traffic than NO2 is within Newcastle.

Figure 3.10 - PM10 Source Apportionment at Jesmond Road (Cradlewell continuous monitor) – Background Contribution Detail

Newcastle Centre

Only the breakdown of PM10 and PM2.5 background contributions is provided for Newcastle Centre as this is an urban background site.

Figure 3.11 shows the breakdown of PM10 background contributions at Newcastle Centre from DEFRA background maps and Figure 3.12 shows the same for PM2.5. 62% of background PM10 concentrations and 59% of background PM2.5 concentrations at Newcastle Centre are categorised as “Other”. The source contribution of PM10 and PM2.5 are very similar, with PM2.5 having a slightly increased contribution from domestic sources, and a slightly decreased contribution from industry.

Figure 3.11 - PM10 Source Apportionment at St Mary’s Place (Newcastle City Centre continuous monitor) – Background Contribution Detail

Figure 3.12 - PM2.5 Source Apportionment at St Mary’s Place (Newcastle City Centre continuous monitor) – Background Contribution Detail

Newcastle upon Tyne has naturally elevated PM10 and PM2.5 concentrations due to it being eight miles from the coast. Of the 61% and 62% of “other” sources of PM10 at Jesmond Road and Newcastle Centre, respectively, the majority is attributed to salt particles in the air with 33% for both locations, but this source is usually larger than 2.5µm, so it only makes up 12% of the PM2.5 at Newcastle Centre. Secondary particulate matter contributes to the majority with 40%. Secondary particulate matter is not emitted directly from sources. It is formed in the atmosphere as a result of chemical reactions that lead to the formation of substances of low volatility which consequently condense into the solid or liquid phase, becoming particulate matter.

## Required Reduction in Emissions

### Required Reduction

In line with the methodology presented in LAQM.TG(22), the necessary reduction in road NOx emissions required to bring the AQMA 1b into compliance are calculated below. This is done at the location of highest exceedance where there is relevant exposure for the declared AQMA which is Market Street (DT8).

Table 3.2 provides the details on the calculations of the NOx emission reduction at Market Street (DT8). The reduction in NOx required to achieve compliance with the annual mean NO2 objective of 36.0 µg/m3 (due to the uncertainty inherent in diffusion tube monitoring methods, concentrations within 10% of the annual mean objective are not considered compliant for LAQM purposes) at the worst-case location of DT8 is 13.5%. This reduction would achieve the compliance needed at the worst-case location within the AQMA 1b.

Table 3.2 – Required NOx emission reduction at the worst-case receptor location in AQMA 1b (Market Street (DT8))

| Metric | Value (concentrations as µg/m3) |
| --- | --- |
| Worst-case relevant exposure NO2 concentration | 38.5 |
| Background NO2 | 16.1 |
| Road NOx – Current | 58.7 |
| Road NOx – required (to achieve NO2 concentration of 36.0 µg/m3) | 50.8 |
| Required road NOx reduction | 7.9 |
| Required % reduction | 13.5% |

### Future Baselining

Potential future emissions at Market Street have been identified across the duration of the Air Quality Action Plan.

A projection of annual mean NO2 concentrations up to 2030 was undertaken at Market Street, using the EFT, to show the possible decrease in concentrations with the 2024 ANPR traffic data.

Traffic Growth using TEMPro

TEMPro (Trip End Model Presentation Program) is software supplied by the Department of Transport which is used to view the NTEM (National Trip End Model) data set which provides forecasts of growth in vehicle journeys. NTEM data can be downloaded for a range of geographical scales from the whole country down to individual lower layer super output areas (LSOAs), for 2011 to 2051 and multiple vehicle types. For this assessment, v8.0 core scenario data for Newcastle upon Tyne from 2024 to 2030 for car journeys on A Roads were used to calculate Adjusted Local Growth Factors for each future year based on a base year of 2024. The Local Growth Factors are shown in Table 3.3 alongside the two-direction traffic flow following the application of the relevant factor. A limitation of this methodology is that the TEMPro Growth Factors are only based on car journeys, however, these factors have been applied to the total traffic flow. It is noted that these factors do not consider the effects of any specific future schemes.

Table 3.3 – Local Traffic Growth Factors from TEMPro

| Year | Local Growth Factor Year-to-Year | Two direction traffic flow on Market Street |
| --- | --- | --- |
| 2024 | - | 2,928* |
| 2025 | 1.0062 | 2,946 |
| 2026 | 1.0177 | 2,980 |
| 2027 | 1.0282 | 3,011 |
| 2028 | 1.0386 | 3,041 |
| 2029 | 1.0491 | 3,072 |
| 2030 | 1.0595 | 3,102 |
| Note: * 2024 ANPR data |  |  |

Projected Emissions

The EFT v13.1 was run for each year between 2025 and 2030 using the in-built fleet projection tool. The traffic data with bespoke Euro fleet and fleet data from the ANPR study was projected to the relevant year using national expectations of fleet turnover (the removal of older vehicles and replacement with newer vehicles). The national projections are considered appropriate for use as the national fleet was found to be similar to the local fleet by the ANPR study, so it is a reasonable assumption that this will continue into the future. It was necessary to simplify the ANPR-built fleet model of 2024 which was used for source apportionment. This was to ensure consistency with the fleet projection tool (which only considers Euro 6 as a whole, rather than by subclass).

It should be noted that the fleet projection tool just considers changes in the Euro classes; no shift in fleet composition (such as an increase in EVs) has been assumed. This can be considered a conservative approach as in reality some degree of increased electrification of the fleet is likely, however there are substantial uncertainties about the speed of uptake. The results are presented in Table 3.4, and shown in Figure 3.13.

Table 3.4 – Projected NOx Emissions for Market Street

| Year | NOX emissions from EFT (g/km/s) |
| --- | --- |
| 2024 | 0.04664 |
| 2025 | 0.04349 |
| 2026 | 0.04087 |
| 2027 | 0.03859 |
| 2028 | 0.03629 |
| 2029 | 0.03478 |
| 2030 | 0.03334 |

Figure 3.13 - Percentage change of emissions based on 2024 at Market Street

The above table and figure show reductions in emissions are predicted from 2024; the emissions could reduce by approximately 29% at Market Street by 2030 compared to 2024.

Translating the predicted reductions in NOx emissions to annual mean NO2 concentrations shows that compliance is predicted to be achieved in 2026 at Market Street with a reduction of 12.4% in NOx emissions compared to 2024 which, combined with predicted reductions in background concentrations, is sufficient to bring the predicted NO2 concentration below 36 µg/m3  as shown in Table 3.5.

Table 3.5 – Predicted reductions in annual mean NO2 concentrations at Market Street

| Metric | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Total NO2 concentration | 38.5 | 36.4 | 34.7 | 33.2 | 31.6 | 30.4 | 29.2 |
| Background NO2 concentration (sector-removed) | 15.8 | 15.3 | 14.8 | 14.4 | 13.9 | 13.5 | 13.0 |
| Road-source NO2 concentration | 22.7 | 21.2 | 19.9 | 18.8 | 17.7 | 16.9 | 16.2 |
| NOx emissions | 0.04664 | 0.04349 | 0.04087 | 0.03858 | 0.03629 | 0.03478 | 0.03334 |
| Year-to-Year percentage reduction |  | 6.75% | 6.03% | 5.58% | 5.94% | 4.16% | 4.15% |

Other potential influences

The projection of traffic flows and NOx emissions is based on simple projection factors that do not consider the Tyne Bridge closure, local developments, such as a potential pedestrianisation of Blackett Street, or how meteorological conditions could influence NO2 concentrations.

It is not confirmed at this time how traffic flows have changed due to the bridge restrictions, or how they may change once the bridge restrictions are lifted; however, the traffic management will need to consider the revised junction on the Gateshead side where the viaduct was closed to traffic in December 2024 and is awaiting demolition, and where city centre buses may be rerouted if Blackett Street is closed. In each case, these potential outcomes will be screened to determine where targeted local air quality assessments are required.

## Key Priorities

Priority areas for the lifetime of this AQAP are shown below. Table 5.1 provides details of all measures proposed to achieve these priorities.

- Priority 1 – To achieve compliance with the NO2 annual mean objective within the AQMA and maintain compliance for at least three years to enable revocation of the AQMA.

- Priority 2 - To achieve compliance with the NO2 annual mean Limit Values within the CAZ and work towards revocation of the CAZ.

- Priority 3 – Collaboration with North East Combined Authority (NECA) on transport related issues, including the electrification of buses.

# Development and Implementation of Newcastle City Council AQAP

## Consultation and Stakeholder Engagement

Section 4.1 and Appendix A to be completed in Final AQAP.

In developing/updating this AQAP, we have worked with other local authorities, agencies, businesses and the local community to improve local air quality. Schedule 11 of the Environment Act 1995, as amended by the Environment Act (2021), requires local authorities to consult the bodies listed in Table 4.1. <insert text here, e.g. In addition, we have undertaken the following stakeholder engagement:

- Website

- Articles in local newspaper

- Questionnaires distributed directly to households along major roads

- Etc.>

The response to our consultation stakeholder engagement is given in Appendix A: Response to Consultation.

Table 4.1 ‒ Consultation Undertaken

| Consultee | Consultation Undertaken |
| --- | --- |
| The Secretary of State | <Yes/No> |
| The Environment Agency | <Yes/No> |
| National Highways | <Yes/No> |
| All neighbouring local authorities | <Yes/No> |
| Any National Park authority as appropriate | <Yes/No> |
| The County Councils (if a District Council) | <Yes/No> |
| Other public authorities as appropriate, such as Public Health officials | <Yes/No> |
| Bodies representing local business interests and other organisations as appropriate | <Yes/No> |

## Steering Group

A steering group was established at the start of the update process to drive forward the development of the new AQAP. The core aim of the steering group was to identify measures for inclusion within the AQAP that would be effective both in terms of reducing NO2 concentrations and also feasible in terms of implementation and delivery.

An AQAP steering group was held on 12/09/2025. Measures identified in Table 5.1 were discussed and examined. Attendees were from:

- Newcastle City Council Public Safety and Regulation;

- North East Combined Authority (NECA);

- Newcastle City Council Transport Planning;

- Newcastle City Council City Transport;

- Newcastle City Council Policy; and

- Newcastle City Council Capital Investment and Growth.

# AQAP Measures

Table 5.2, later in this section shows the Newcastle City Council AQAP measures. It contains:

- A list of the actions that form part of the plan;

- The departments/organisations responsible for delivering this action;

- Estimated cost of implementing each action;

- Expected benefit in terms of pollutant emission and/or concentration reduction;

- The timescale for implementation; and

- How progress will be monitored.

NB: Please see future Annual Status Reports (ASRs) for regular annual updates on implementation of these measures.

Further information on the cost-benefit analysis of these measures is provided below.

## Cost Benefit Analysis

A long list of potential measures was drawn up based upon the key priorities, previous work undertaken by the Council, and the priorities of Steering Group members.

A cost benefit analysis was carried out for the short list of actions. Four aspects were considered in this analysis:

- The feasibility of carrying out the action, i.e. is there likely to be public or internal support, is there an available funding source.

- The air quality impact of the action, i.e. how large of an impact could this measure have on concentrations of pollutants on a local and/or regional level. This is based on professional judgement and a review of available literature where possible.

- Any co-benefits arising from this action, i.e. are there also benefits for public health, active travel, climate, the economy, or society more widely; and

- High level assessment of the cost of this action.

Each aspect was rated from 1 to 3, where 1 is low and 3 is high and then the following equation was applied to calculate a total score for each measure:

Score = (feasibility + (2 x air quality impact) + co-benefits) x cost

The air quality impact of the action was double rated compared to feasibility and co-benefits as this is the primary focus of the AQAP.

For the scoring of the cost, the following categories were used: less than £10,000, between £10,000 and £100,000, and greater than £100,000.

The short list measures and their scores are presented in Table 5.1. Further information on the measures not taken forward and the reasoning for that are provided in Appendix B.

Table 5.1 ‒ Cost Benefit Analysis of short-listed actions

| Number | Measure | Feasibility | AQ impact | Co benefit | Score | Cost | Cost Score |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Clean Air Zone | 3 | 3 | 1 | 10 | 1 | 10 |
| 2 | Bus Electrification | 2 | 3 | 2 | 10 | 1 | 10 |
| 3 | Exposure Limitation at Stephenson Road | 2 | 3 | 1 | 9 | 2 | 18 |
| 4 | Local Plan | 3 | 2 | 2 | 9 | 3 | 27 |
| 5 | Movement Strategy | 3 | 2 | 2 | 9 | 3 | 27 |
| 6 | Active Travel Investment | 2 | 2 | 3 | 9 | 1 | 9 |
| 7 | Travel Cards | 3 | 2 | 2 | 9 | 3 | 27 |
| 8 | Smoke Control Area Education and Enforcement | 3 | 2 | 2 | 9 | 3 | 27 |
| 9 | Car Club | 2 | 2 | 2 | 8 | 2 | 16 |
| 10 | Electric charging infrastructure | 1 | 2 | 2 | 7 | 1 | 7 |

Three measures have been identified as the ‘top three’ air quality actions due to their high scores and because they scored the maximum for the air quality impact as identified by the cost benefit analysis, and these actions are prioritised for further detailed information in Sections 5.3 and 6. All actions are presented in order of descending order score (before cost considerations).

Table 5.2 ‒ Air Quality Action Plan Measures

| Measure No. | Measure | Category | Classification | Estimated Year Measure to be Introduced | Estimated / Actual Completion Date | Organisations Involved | Funding Source | DEFRA AQ Grant Funding | Funding Status | Estimated Cost of Measure | Measure Status | Target Reduction in Pollutant / Emission from Measure | Key Performance Indicator | Progress to Date | Comments/Potential Barriers to Implementation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Priority Targeted Measures |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Clean Air Zone | Promoting Low Emission Transport | Low Emission Zone (LEZ) | 2023 | 2023 | NCC | NCC | No | Funded | > £10 million | Ongoing | Reduction of up to 15.5 µg/m3 in annual mean NO2 concentration | Number of non-compliant vehicles travelling within CAZ area | CAZ was partially implemented in January 2023 and was fully operational in July 2023 | - |
| 2 | Bus Electrification | Vehicle Fleet Efficiency | Promoting Low Emission Public Transport | 2026 | 2030 | NCC, NECA | LUF, ZEBRA 2, TBC | No | Partially Funded | > £10 million | Ongoing | Reduction of up to 2.9 µg/m3 in annual mean NO2 concentration | Number of zero emissions buses | - | Potential barriers to implementation are cost and the need for host infrastructure at the depot locations such as charging points, together with a recognition of short to medium term challenges of the range of those vehicles, especially those long-distance services such as the buses going into Northumberland and Eldon Square into County Durham. |
| 3 | Exposure Limitation at Stephenson Road | Other | Other | 2026 | 2030 | NCC | NCC | No | Partially Funded | £50k - £100k | Not started | Quantification work in process | Compliance with short-term mean NO2 objective and annual mean Limit Value | - | NCC is commissioning work into identifying whether pavement diversion or barriers would be successful in reducing short-term exposure on Stephenson Road |
| Supportive Strategic Measures |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Local Plan | Policy Guidance and Development Control | Air Quality Planning and Policy Guidance | 2028 | N/A | NCC | NCC | No | Funded | <£10k | In progress | Direct LAQ benefit not quantifiable. | Production of Local Plan | - | The new joint Newcastle-Gateshead Local Plan is at an early stage of development. Air quality will be considered throughout the development lifecycle. |
| 5 | Movement Strategy | Policy Guidance and Development Control | Other policy | 2026 | N/A | NCC | NCC | No | Funded | <£10k | In progress | Direct LAQ benefit not quantifiable. | Production of Movement Strategy | Consultation held in late 2024 | This strategic framework will guide long-term planning of transport in Newcastle up to 2045. Includes aim to “create safer and more vibrant places for people to live, work, study, and play by reducing traffic and improving air quality”. |
| 6 | Active Travel Investment | Promoting Travel Alternatives | Other | 2030 | N/A | NCC, NECA | TBC | No | Partially Funded | £500k - £1 million | In progress | No specific target reduction identified | Miles of active travel infrastructure | - | Ongoing investment in walking and cycling infrastructure in line with the North East Active Travel Strategy There is potential for knock-on air quality impacts of active travel schemes / public realm works for example when they involve the diversion of road traffic. These potential outcomes will be screened to determine where targeted local air quality assessments are required. |
| 7 | Travel Cards | Promoting Travel Alternatives | Other | 2025 | N/A | NCC, NECA, Nexus | Nexus | No | Funded | <£10k | In progress | Direct LAQ benefit not quantifiable. | Number of travel cards issued | Travel card schemes in place | Nexus Corporate Metro Season Ticket scheme. Concessionary passes available for children, older people and people with disabilities. |
| 8 | Smoke Control Area Education and Enforcement | Other | Other | 2025 | N/A | NCC Environmental Health | NCC | No | Funded | < £10k | In progress | Direct LAQ benefit not quantifiable. | Number of complaints | - | Encourage the correct use of solid fuel appliances |
| 9 | Car Club | Alternatives to private vehicle use | Car Clubs | 2025 | N/A | NCC, Enterprise | NCC | No | Partially Funded | £50k - £100k | In progress | Reduction of up to 72.8% in annual NOx emissions | Number of car club bays | 30 car club bays across the city; 1 electric | NCC is identifying funding sources to install EV charging points in bays. |
| 10 | Electric charging infrastructure | Promoting Low Emission Transport | Procuring alternative Refuelling infrastructure to promote Low Emission Vehicles, EV recharging, Gas fuel recharging | 2030 | N/A | NCC, NECA | TBC | No | Not funded | £500k - £1 million | In progress | Reduction of up to 32.2 kg/yr of NOx emissions | Number of chargers installed | Range of rapid and standard chargers installed. | Residential electric vehicle charging infrastructure is expected to be funded by the Local Electric Vehicle Infrastructure Fund (LEVI) which is managed by NECA. NECA also supports Newcastle City Council to deliver charging at destination locations using the Levelling Up Funding and City Region Sustainable Transport Settlement. These are typically rapid or fast chargers. |

## Timescales of the AQAP Measures

Many of the measures set out Table 5.1 are already in progress with a few in the planning phase. Timescales are provided in Table 5.1. Further timescale information for the top three actions is provided here.

For measure 1 – Clean Air Zone, a Government mandated Clean Air Zone (CAZ) was implemented in part of Newcastle and Gateshead in January 2023 and fully operational in July 2023. The CAZ will remain in place until compliance with the NO2 annual mean Limit Value is achieved.

For measure 2 – Bus Electrification, 10 bus services operated by three bus operators (the 21, X66, and 58 of Go North East, the 43, 44/45, 48, 64, and X46 of Arriva, and the 30/31 and 36 of Stagecoach) are expected to be electrified by March 2026.

NCC will collaborate with its identified Air Quality Partner, NECA, in the medium to longer term as further funding opportunities become available, to continue to push for increased electrification of buses in Newcastle.

Finally, for measure 3 - Exposure Limitation at Stephenson Road, work to identify whether pavement diversion or barriers would be successful in reducing short-term exposure on Stephenson Road is currently commissioned and will be completed in 2026, and the results of the study will inform subsequent work timelines.

## Air Quality Partners

NECA has been identified as an Air Quality Partner in the delivery of this AQAP, due to its responsibilities with respect to buses in Newcastle. Buses have been identified as the primary contributor to the remaining exceedances of the annual mean NO2 objective in the city centre. Therefore, electrifying the bus fleet is a key priority action for which we have identified that NECA are the responsible party.

## Maintaining Safe Air Quality

Newcastle City Council will continue to monitor local air quality throughout their jurisdiction and review and report annually within the ASRs as required by LAQM regulations to ensure the objectives are achieved and maintained in the future. If new areas of concern arise, for example due to new development, or worsening congestion, additional monitoring will be installed to monitor these changes.

All new developments which have the potential to result in significant air quality impacts on or off-site will require an air quality assessment in line with the local plan. Additionally, industrial developments which result in emissions to air will be subject to the Permitting Regulations. Together, the planning and permitting regimes will ensure that new developments are consistent with the maintenance of air quality standards.

Following three years of compliance with the AQO and the revocation of the AQMA, an Air Quality Strategy (AQS) will be produced and implemented to continue improving air quality and public health after the objectives have been achieved.

# Quantification of Measures

## Measure 1 – Clean Air Zone

For the full business case for the Clean Air Zone (CAZ), modelling was undertaken to predict the reduction in annual mean NO2 concentrations. It should be noted that only Pollution Climate Mapping (PCM) road links were modelled, therefore, the city centre of Newcastle was not modelled. The only modelled PCM link of relevance is PCM link 47526 which is located on Stephenson Road and is adjacent to the diffusion tube monitoring location DT81.

Table 6.1 shows the modelled annual mean NO2 concentrations in 2023 with and without the CAZ in place with an indicative value of 90% compliance across multiple scenarios and sensitivity tests. The actual measured annual mean NO2 concentration at DT81 was considerably higher in 2023 with 67.1 µg/m3. This is due to multiple reasons:

- In the full business case the compliance with the CAZ was modelled with approximately 90% in 2023, however, the actual compliance was lower with approximately 80% in 2024. A more detailed breakdown of the actual compliance can be found below;

- The receptor for PCM link 47526 was modelled 4m from the kerb, however, DT81 is located 1m from the kerb; and

- Local conditions were not recognised in the full business case model, such as queuing and canyoning, which may have contributed to the ongoing high concentrations.

Table 6.1 ‒ Modelled annual mean NO2 concentrations for PCM link 47526 in 2023

| Modelled Link | Annual mean NO2 concentration in 2023 without the CAZ | Annual mean NO2 concentration in 2023 with the CAZ |
| --- | --- | --- |
| PCM link 47526 | 49.9 µg/m3 | 34.4 µg/m3 |

A CAZ Triage Report was submitted to the Joint Air Quality Unit (JAQU) in summer 2025 after the outcome of the Stage 1 assessment. The report compared the CAZ model predictions for traffic and emissions in 2023 with the actual recorded traffic and calculated emissions in 2024. It was concluded that there is a strong similarity in traffic breakdown and source apportionment, indicating that the model was effective in forecasting traffic and emissions. Therefore, effects of the CAZ were broadly in line with the modelling.

The Triage Report also determined the compliance in terms of emissions classification (Euro class and fuel type) of vehicles entering the CAZ in 2024. The CAZ implemented is a class C that charges all buses, coaches, taxis, private hire vehicles (PHVs), heavy good vehicles (HGVs), vans and minibuses that do not meet the Euro 6/VI emission standards for diesel and Euro 4 for petrol. To determine the proportion of compliant and non-compliant vehicles the 2024 ANPR data was analysed. Figure 6.1 shows the proportion of compliant and non-compliant vehicles in 2024, and the majority of vehicles are compliant. Only the buses are lagging compliance with 49.9% of buses entering the CAZ being non-compliant. It is to be noted that this will impact annual mean NO2 concentrations within the city centre, especially at Market Street (DT8) which is currently not compliant. Therefore, the electrification of the bus fleet is the second priority measure.

Figure 6.1 - Proportion of compliant and non-compliant vehicles entering the Clean Air Zone in 2024

The Emissions Factor Toolkit v13.1 was used to project the euro class breakdown of the fleet based on the 2024 ANPR data into the future up to 2030. Figure 6.2 shows the projected proportion of compliant and non-compliant diesel cars, diesel LGVs and buses entering the CAZ from 2025 – 2030. By 2030 the compliance is predicted to further increase with the maximum of 27% increase of compliance for buses.

Figure 6.2 - Projected proportion of compliant and non-compliant Diesel Cars, Diesel LGVs and Buses entering the Clean Air Zone from 2025 – 2030

The reduction in annual mean NO2 concentrations and the increase in vehicle compliance are evidence of the effect which the CAZ has had up to now. The CAZ will stay in place until compliance with the annual mean NO2 Limit Value is achieved. The benefits of the CAZ will continue to be felt into the future over the lifetime of this AQAP by restricting access to old and polluting vehicle types.

## Measure 2 – Electrifying the bus fleet

NECA has provided a delivery plan of electrifying the bus fleet in 2026. The services being electrified going past the two exceeding locations, Market Street (DT8) and St Mary’s Place (DT5/115/116), have been identified and the number of average daily buses calculated based on the timetables available as shown in Table 6.2. The Service 21, 58 and 30/31 go past DT8 while only Service 21 and 30/31 also go past DT5/115/116. The delivery plan is predicted to result in 17.3% of buses that go past DT8 and DT5/115/116 to be electrified in 2026 (Table 6.3).

Table 6.2 ‒ Average daily buses going through Market Street and St Mary’s Place that are part of the bus electrification plans

| Bus Service | Number of Average Daily Buses |
| --- | --- |
| Service 21 | 1091 |
| Service 58 | 202 |
| Service 30/31 | 403 |
| Note: 1 based on the available timetable here: Angel 21 - Newcastle to Durham and Brandon ¦ Go North East 2 based on the available timetable here: East Gateshead Rider 58 - Newcastle to Heworth and Follingsby Amazon ¦ Go North East 3 based on the available timetable here: 30 Bus Route & Timetable: Fenham - Fawdon, Montagu Estate or City Centre ¦ Stagecoach |  |

Table 6.3 ‒ Proportions of buses to be electrified in 2026

| Monitoring location | Total Number of Diesel Buses in 2026 | Total Number of Buses being electrified in 2026 | % Proportion of electrified buses in 2026 |
| --- | --- | --- | --- |
| Market Street (DT8) | 9791 | 1692 | 17.3% |
| St Mary’s Place (DT5/115/116) | 8621 | 1492 | 17.3% |
| Note: 1 based on the TEMPro local traffic growth factors 2 sum of average daily buses |  |  |  |

It is predicted that the bus electrification will result in a reduction of total NOx emissions of 14.7% and 13.1% for Market Street and St Mary’s Place, respectively, which translates in a reduction in annual mean NO2 concentrations of 2.9 µg/m3 and 2.4 µg/m3, respectively (Table 6.4).

Table 6.4 ‒ Predicted annual mean NO2 concentrations at Market Street and St Mary’s Place with and without the bus electrification in 2026

| Metric | 2024 | 2025 | 2026 |
| --- | --- | --- | --- |
| Market Street without bus electrification |  |  |  |
| Total NO2 concentration | 38.5 | 36.4 | 34.7 |
| NOx emissions | 0.04664 | 0.04349 | 0.04087 |
| Market Street with bus electrification |  |  |  |
| Total NO2 concentration | 38.5 | 36.4 | 31.8 |
| NOx emissions | 0.04664 | 0.04349 | 0.03484 |
| St Mary’s Place without bus electrification |  |  |  |
| Total NO2 concentration | 36.3 | 34.4 | 32.8 |
| NOx emissions | 0.06121 | 0.05708 | 0.05351 |
| St Mary’s Place with bus electrification |  |  |  |
| Total NO2 concentration | 36.3 | 34.4 | 30.4 |
| NOx emissions | 0.06121 | 0.05708 | 0.04653 |

## Measure 3 – Exposure Limitation at Stephenson Road

DT81 at Stephenson Road measured an annual mean NO2 concentration of 64.5 µg/m3 in 2024, potentially exceeding the 1-hour mean NO2 objective.

However, DT81 was calculated to be compliant with the annual mean NO2 objective at relevant exposure with 35.8 µg/m3 (Table 6.5).

Table 6.5 – Non-automatic NO2 Fall off With Distance Calculations (concentrations presented in µg/m3)

| Site ID | Distance (m): Monitoring Site to Kerb | Distance (m): Receptor to Kerb | Monitored Concentration (Annualised and Bias Adjusted | Background Concentration | Concentration Predicted at Receptor | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| DT81 | 1.0 | 16.0 | 64.5 | 13.1 | 35.8 |  |

New monitoring adjacent to the residence behind DT81 has been set up to confirm the distance correction calculation that the annual mean objective is not exceeded at this location.

LAQM.TG(22) provides examples of where the 1-hour mean air quality objective should apply. For example, it should apply at kerbside sites such as pavements of busy shopping streets, however, it should not apply at kerbside sites where the public would not be expected to have regular access.

The pavement on which DT81 is located would not be expected to have regular access because it is a dead end. Therefore, DT81 is not considered to be located at relevant exposure for the 1-hour mean NO2 objective. There is a cycle path and footpath just behind DT81 which may be considered relevant exposure points for the 1-hour mean NO2 objective and further work has been commissioned to identify the risk of exceedance and potential mitigation measures such as erecting an air quality barrier, with quantification therefore to be provided at a later date.

## Measure 6 – Car Clubs

Studies have found that one car club car can replace between 4 to 26 privately owned vehicles,,,, although the number of private cars replaced by a car club vehicle is highly dependent on the environment in which it operates16,.

Therefore, to estimate the NOx emissions savings of a car club car in Newcastle the EFT v13.1 was run with:

- 15 cars (predicted number of privately owned cars that may be replaced by a single Car Club car); and the bespoke Euro Fleet for Newcastle; and,

- One petrol Car Club vehicle, assumed to be a petrol Euro 6 class (Euro 6 d/e).

It is estimated that one Car Club car could save 72.8% in annual NOx emissions by replacing 15 privately owned vehicles as demonstrated in Table 6.6.

Table 6.6 – Annual NOx emissions savings from one Euro 6 Car Club car replacing 15 privately owned vehicles

| Annual NOx emissions of 15 typical cars in Newcastle (kg/yr) | Average annual milage (km) | Annual NOx emissions of one Euro 6 petrol Car Club car (kg/yr) | Average annual milage (km) | Annual NOx emissions savings with one Euro 6 Car Club Car (kg/yr) |
| --- | --- | --- | --- | --- |
| 6,497.71 | 7,3002 | 1,769.13 | 109,5004 | 4,728.6 |
| Note: 1 based on 2024 ANPR data 2 DfT (2024), Anonymised MOT tests and results, average of 2019 and 2023, excluding Covid-19 years 3 based on a petrol Euro 6 d/e car 4 average annual milage multiplied by 15 to replace milage of 15 privately owned cars |  |  |  |  |

## Measure 8 – Electric charging infrastructure

Zapmap routinely published a summary of the public charge point utilisation. These numbers were used to calculate the total mileage travelled by an Electric Vehicle (EV) daily as shown in Table 6.1. The EFT v13.1 was run with a nominal car and the Bespoke Euro Fleet of Newcastle to calculate the annual NOx emission savings that may be achieved by provision of one ultra rapid charger.

Using a cautious charge rate (i.e. relatively low speed) output of 50 kWh, the NOx emissions were estimated to be equivalent to 32.2 kg/yr.

Table 6.7 – Calculation of total mileage travelled daily by an Electric Vehicle (EV) charged at a ultra rapid charger of 50kWh +

| Average number of charge sessions per day | Average session duration (min) | Total kWh provided if 50 kWh output | Average EV car energy consumption per km (kWh) | Total mileage travelled daily (km) |
| --- | --- | --- | --- | --- |
| 3.71 | 371 | 114.12 | 0.210283 | 542.5 |
| Note: 1 Zapmap (2025). Public charge point utilisation. Available at: Public charge point utilisation - Zapmap 2 This provides a bottom-end estimate as 50 kWh output was used for the calculation. However, ultra rapid chargers can output up to 150 kWh. 3 Department for Energy Security and Net Zero (2024). Greenhouse gas reporting: conversion factors 2024. Available at: Greenhouse gas reporting: conversion factors 2024 - GOV.UK |  |  |  |  |

## Overall Quantification

Newcastle City Council expects that overall, with full implementation of the plan that compliance will be achieved in 2026.

- Appendix A: Response to Consultation

Table A.1 ‒ Summary of Responses to Consultation and Stakeholder Engagement on the AQAP

| Consultee | Category | Response |
| --- | --- | --- |
| <Insert consultee> | <Insert category> | <Insert text> |

- Appendix B: Reasons for Not Pursuing Action Plan Measures

Table B.1 ‒ Action Plan Measures Not Pursued and the Reasons for that Decision

| Action category | Action description | Reason action is not being pursued (including Stakeholder views) |
| --- | --- | --- |
| Traffic Management | Parking permits and enforcement | 18,000 residents/visitor parking permits have been issued. The Council holds parking enforcement powers. However, benefits on air quality are likely to be small and are difficult to quantify. |
| Promoting Travel Alternatives | Park and Ride | Park and Ride facilities are already provided at Metro Stations |
| Promoting Travel Alternatives | Encourage/facilitate home working | Since Covid-19 home working and flexible working hours are already occurring. |
| Vehicle Fleet Efficiency | Taxi Emissions | Reducing the emissions of taxis is captured in the Clean Air Zone. |
| Vehicle Fleet Efficiency | Eco driving training | This measure would be unfunded with negligible benefits with regard to specific locations of concern. |
| Freight and Delivery Management | Delivery times outside peak hour | This is already implemented in some city centre locations. However, this action is likely to achieve negligible quantifiable benefits to local air quality. |
| Traffic Management | Speed Restrictions | Twenty’s Plenty advisory scheme already rolled out in selected areas. Further air quality benefits are likely to be very small. |
| Traffic Management | Closing roads to reduce congestion on Stephenson Road | Roads / junctions cannot feasibly be closed for traffic without significant network impacts |
| Traffic Management | Gating traffic and traffic calming to manage traffic at hot spots | Limited opportunity to gate traffic due to risk of creating emissions hot spots elsewhere |

- Appendix C: Planning and Policy Detail

C.1 National Planning and Policy Context

#### Environment Act (2021)

The Environment Act 2021 amends the Environment Act 1995 and sets a new course for the UK’s environmental policy post-Brexit. It includes provisions to establish a set of statutory environmental principles to guide future legislation and policy decisions and ensure environmental governance through an environmental watchdog, the Office for Environmental Protection (OEP).

Under Part IV of the Act, the government is mandated to develop a National Air Quality Strategy (AQS) which contains clear standards, objectives, and measures to improve ambient air quality, and to publish a report reviewing the AQS every five years (as a minimum and with yearly updates to Parliament), in the form of the Environmental Improvement Plan.

The Environment Act 2021 includes a proposal that the government set a range of new environmental targets including an annual mean concentration target and a population exposure reduction target for PM2.5. Following through on these requirements, the Environmental Targets (Fine Particulate Matter) (England) Regulations 2023 came into effect, introducing the two targets described above. These legislative targets must be met at relevant monitoring stations by December 31, 2040. Full guidance on how target values should be considered in development control and local air quality control is not yet available. Interim Planning Guidance was published in October 2024. The guidance moves away from an exceedance-based approach and towards a minimisation of pollution approach. It recommends key sources of air pollution schemes submitted for planning applications are identified, and appropriate action to minimise emissions of PM2.5 and its precursors are implemented as far as is reasonably practicable. If quantitative evidence is not available, a qualitative approach can be taken.

#### Clean Air Strategy

In 2019, the UK government introduced the Clean Air Strategy 2019, a major component of its broader 25 Year Environment Plan, and the government’s primary strategy for air quality. This strategy underscored a renewed governmental commitment to air quality improvements and also laid the groundwork for the development of more recent legislative changes as described above.

In recent years, air quality management has primarily focused on nitrogen dioxide (NO2), and its principal source in the UK i.e. road traffic. However, the Clean Air Strategy broadens the focus to other areas. This shift in emphasis is part of a longer-term goal to reduce the levels of PM2.5 in ambient air. It outlined comprehensive measures to combat air pollution, from reducing emissions across various sectors to enhancing the country's monitoring and analytics capabilities. Recognizing that air pollution is a complex problem influenced by a range of factors, including industrial activity, agriculture, and domestic heating, the strategy advocated for a holistic approach to ensure cleaner air.

#### Air Quality Strategy 2023

Functioning as a framework for local authority delivery of the above plans, a new Air Quality Strategy (AQS) was published in April 2023. This updated strategy is action-oriented, outlining specific roles for local authorities in support of achieving the new national PM2.5 targets and other long-term air quality goals. It specifies that local authorities are expected to take action by controlling emissions from sources within their jurisdiction.

The AQS outlines proposals to tackle emissions from a range of sources. This includes providing clear and effective guidance on how an Air Quality Management Areas (AQMAs), Clean Air Zones (CAZs) and Smoke Control Areas interrelate and how they can be used by local government to tackle pollution.

#### National Planning Policy Framework (2024)

The National Planning Policy Framework (NPPF) sets out the Government’s environmental, economic and social policies and principles for land use planning in England and how these are expected to be applied, providing a framework within which locally-prepared plans for development can be produced. The National Planning Policy Framework was first published in March 2012, and was last updated in December 2024.

Paragraphs 110, 187, and 199 and 224 of the NPPF provide advice on when air quality should be a material consideration in development management decisions.

Paragraph 199 states that:

“Planning policies and decisions should sustain and contribute towards compliance with relevant limit values or national objectives for pollutants, taking into account the presence of Air Quality Management Areas and Clean Air Zones, and the cumulative impacts from individual sites in local areas. Opportunities to improve air quality or mitigate impacts should be identified, Opportunities to improve air quality or mitigate impacts should be identified, such as through traffic and travel management, and green infrastructure provision and enhancement. So far as possible these opportunities should be considered at the plan-making stage, to ensure a strategic approach and limit the need for issues to be reconsidered when determining individual applications. Planning decisions should ensure that any new development in Air Quality Management Areas and Clean Air Zones is consistent with the local air quality action plan.”

#### Integrated National Transport Strategy (emerging)

The Department for Transport is developing a strategy which will set the high-level direction for how transport should be designed, built and operated in England over the next 10 years. It will set out a single national vision which will:

- Put people who use transport and their needs at its heart; and

- Empower local leaders to deliver integrated transport solutions that meet the needs of their local communities.

A call for evidence ran from 28th November 2024 to 20th February 2025. A series of regional roadshows were held in February and March 2025 for the government to listen to ideas on how the strategy can support better integrated public transport and improve transport in rural areas, learning from successful integrated systems such as the Bee Network, as well as considering how cycling and walking can become the best choice for shorter journeys. Another call for evidence is currently underway until 16th October 2025.

#### Net Zero Strategy: Build Back Greener (2021)

The Net Zero Strategy – Build Back Greener was published in October 2021. It sets out policies and proposals for decarbonising all sectors of the UK economy to meet the net zero target by 2050. This strategy builds on the 10-point plan for a green industrial revolution which lays the foundations for a green economic recovery from the impacts of Covid-19. It aims to keep the UK on track for the carbon budgets, the 2030 Nationally Determined Contribution, and net zero by 2050. Key policies in relation to air quality are:

“By 2035 the UK will be powered entirely by clean electricity, subject to security of supply.” p. 19

“An ambition that by 2035, no new gas boilers will be sold.” p. 22

“[…] [the] 2030 commitment to end the sale of new petrol and diesel cars, and 2035 commitment that all cars must be fully zero emissions capable.” p.24

“[…] enable [that] half of journeys in towns and cities to be cycled or walked by 2030.” p. 25

“[…] a net zero rail network by 2050, with the ambition to remove all diesel-only trains by 2040.” p. 25

C.2 Regional Planning and Policy Context

#### North East Local Transport Plan: Delivering Green Transport

The Mayor’s Local Transport Plan (LTP) for the North East sets out the North East Combined Authority’s transport priorities up to 2040 with a list of proposals to create a green, integrated transport network.

Air Quality is discussed in the context of the mission for being the home of the green energy revolution:

“We will help people to make greener journeys by making sustainable travel easier, more affordable, and more attractive, benefitting the environment. We will encourage the switch away from petrol/diesel cars and vans to zero emission cars/vans which will improve air quality across our region.”

Air Quality is also discussed in the context of the UK Government mission for building an NHS fit for the future and how the Local Transport Plan supports the delivery of this:

“Improving health through increased active travel and better air quality. […]”

#### The Interim North East Local Growth Plan 2025

The Interim Plan was published in March 2025 and it intended for wider consultation and input with a final version being published in summer 2025. The 10-year plan sets out how the economy will grow, businesses are supported and living standards are improved.

The five key missions are:

- “Home to a growing and vibrant economy for all;

- Home of the green energy revolution;

- A welcoming home to global trade;

- Home of real opportunity; and

- A North East we are proud to call home”.

Within mission 5 air quality is identified as a challenge to deliver this mission:

“Contrasting transport challenges between rural isolation in more remote areas and poor air quality and congestion in parts of our towns and cities.”

The aim is “to create a green, integrated transport network that works for all”.

#### Go Ultra Low North East

The Go Ultra Low North East programme aims to raise an awareness of Ultra Low Emissions Vehicles or ULEVs, encouraging consumers to consider using electric vehicles (EVs) in the future.

#### North East Active Travel Strategy 2023

In June 2023, the North East Joint Transport Committee approved a new North East Active Travel Strategy covering Tyne and Wear, Northumberland and Durham. The Travel Strategy aims to encourage more active travel – walking, wheeling and cycling – across the North East and sets out proposals to help people travel actively more often. One benefit of over half of all shorter journeys being made by active travel in the North East by 2035 could be:

“Better air quality by reducing pollution from traffic emissions.”

#### Making the Right Travel Choice Strategy 2022

The Making the Right Travel Choice Strategy encourages car users to switch one journey a week to public transport, walking, wheeling, or cycling and for people who do not have access to a car to continue to travel sustainably. The objectives are:

- Carbon neutral North East

  - We will take action to make travel in the North East net carbon zero. We will address our air quality challenges and aim to tackle the climate emergency.

- Overcome inequality and grow our economy

  - We will return the region to pre COVID-19 levels of employment and Gross Domestic Product (GDP), then move towards the ambitions set out in the North East Local Enterprise Partnership’s Strategic Economic Plan (SEP).

- Healthier North East

  - We will encourage active travel (such as cycling, walking and wheeling) to help our region reach public health levels that are at least equal to other parts of the UK.

- Appealing sustainable transport choices

  - We will introduce measures that make sustainable transport a more attractive, and an easy way to get around the North East.

- Safe, secure network

  - We will improve transport safety and security, ensuring that people are confident that they feel safe and secure when travelling.

One benefit of car users switching one journey a week to public transport, walking or cycling and people who do not have access to a car continuing to travel sustainability would

“potentially reduce […] road traffic emissions”.

#### Bus Service Improvement Plan 2023

The North East Bus Service Improvement Plan (BSIP) outlines regionwide ambitions to make buses more attractive by making them an affordable and practical alternative to using private cars for more people and helping existing bus users to travel more frequently.

The plan aims to return bus use – currently 25% lower than before the pandemic – to pre-Covid levels and to grow by 10% each year thereafter.

Increasing the use of buses will help to achieve many objectives such as:

- “lowering carbon emissions;

- improving air quality and public health; and

- connecting people to education, jobs and other opportunities.”

#### Zero Emission Vehicle Strategy 2023

The North East Zero Emission Vehicle Strategy aims to create excellent infrastructure and well-informed people, who can access the right charge points and information when they need it, with the aim to leading to an increase in Zero Emission Vehicles (ZEV), and a reduction in carbon emissions across the region.

Before this strategy was approved in December 2023, the North East Joint Transport Committee approved the first regionwide Zero Emission Vehicle Policy in March 2022. This is an outline of the region’s aim to lead the country in boosting the up-take of Electric Vehicles (EV) by developing and expanding charging facilities.

The delivery of this strategy will help ensure that future public ZEV infrastructure projects:

“are actively promoted, highlighting the benefits to the region, such as reduced CO2 emissions and improved air quality through the complete removal of localised and toxic tailpipe emissions.”

#### Rail and Metro Strategy

The Rail and Metro Strategy outlines the future of rail and Metro in the region with the overall vision to “moving to a green, health, dynamic and thriving North East”.

Some of the key commitments indirectly related to air quality are:

- “Further deliver improved energy efficiency and encourage mode shift from cars to enable more people to travel sustainably”;

- “Improve the customer experience through refurbished and enhanced stations, passenger information and integration with the wide public transport network”;

- “Increasing the number of people travelling on rail and Metro in preference to the private car”;

- “Increasing the share of goods transported by rail”;

- “Introducing new trains, more efficient electric ones on the Metro and electric / battery/ hydrogen ones on local rail and modal shift from road to rail on freight”;

- “Improving walking and cycling links to existing and new stations”; and

- “Increasing the number of people travelling on rail and Metro in preference to the private car”.

C.3 Local Planning and Policy Context

#### Local Plan

Gateshead and Newcastle Councils are currently in the process of preparing a new joint Local Plan. Central government is keen to bring forward partnership working between Local Planning Authorities and Combined Authorities.

The current Local Plan is a collection of documents that guides future development in Newcastle to 2030 which consist of two parts: the Core Strategy and Urban Core Plan (CSUP), and the Development and Allocation Plan (DAP).

The Core Strategy and Urban Core Plan 2010 - 2030 (CSUCP) is a strategic planning framework that guides development in Newcastle and Gateshead to 2030. It is the first part of the councils Local Plan, containing an overall vision and spatial strategy to deliver economic prosperity and create lifetime neighbourhoods. The Plan covers the whole of the area within the administrative boundaries of Gateshead and Newcastle and includes strategic policies and specific policies for the Urban Core, Sub-Areas and sites. The Plan was formally adopted by Newcastle City Council in March 2015.

Air Quality is discussed under policy CS14 Wellbeing and Health:

“The wellbeing and health of communities will be maintained and improved by:

- Requiring development to contribute to creating an age friendly, healthy and equitable living environment through:

[…]

  - Preventing negative impacts on residential amenity and wider public safety from noise, ground instability, ground and water contamination, vibration and air quality,

[…]”

The Development and Allocations Plan 2015 - 2030 (DAP) provides more detailed policies to support growth ambitions for Newcastle including:

- Policies which will be used to make decisions on planning applications;

- Allocations of housing and employment sites to support the DSUCP; and

- Designations of retail centre boundaries and sites for environmental protection.

The Development and Allocations Plan was formally adopted by Newcastle City Council in June 2020.

Air Quality is discussed under policy DM24 Environmental and Health Impacts of Development:

“ Proposals will be required to demonstrate that there is no unacceptable adverse environmental and health impacts (including cumulative impacts) from the development. To achieve this development must assess and mitigate the following environmental and health impacts:

- Air quality and the opportunities to improve air quality;

[…]”

Air Quality is also discussed under policy DM32 Minerals Extraction and Reclamation:

“Development of minerals operations will only be supported where it can be demonstrated that all material social, economic and environmental impacts that would cause demonstrable harm to the natural and historic environment or human health can be acceptably mitigated. Proposals will need to demonstrate no unacceptable adverse impact on:

[…]

- Air quality;

[…]”

#### Newcastle Movement Strategy (emerging)

Newcastle is currently developing the Movement Strategy which will be presented to Cabinet in summer 2025.

The Movement Strategy for Newcastle will supplement the North East Transport Plan, the North East Combined Authority’s core strategy for transport, which sets out the regional ambitions up to 2040 as well as Newcastle and Gateshead’s Local Plan, which sets out how wider development and planning policy will help to shape the city in the coming years.

The Movement Strategy will guide transport development until 2045, creating a transport network that is efficient, safe, accessible and inclusive. One focus point is to improve the wider environment by reducing Newcastle’s carbon footprint.

#### Newcastle Green Infrastructure Strategy

Newcastle produced a Green Infrastructure Strategy in October 2022 which updates the previous strategy from 2011. The Strategy supplements the Local Plan, and reviews and identities the strategic provision of Green Infrastructure which includes open space within the city. Green Infrastructure can have multiple benefits such as clean air. While air quality is not explicitly mentioned within the objectives of the Green Infrastructure Strategy, air quality is part of the vision:

“Our green infrastructure has the potential to offer multiple benefits for people and wildlife. We have a huge challenge in terms of climate change, and green infrastructure has an extremely important role in cooling the urban environment, reducing temperatures by planting large canopy trees, which in turn will improve the air quality. It will play an important role in the Council’s plans to be carbon neutral by 2030. In the context of the global climate emergency, biodiversity loss and health inequalities, investment in the provision of high quality, biodiverse and accessible green and blue infrastructure has never been more vital. Our city will become more equitable, liveable, and resilient by making Newcastle a greener and healthier place.”

#### Net Zero Newcastle 2030 action plan

This Action Plan presents Newcastle’s view of how the city can achieve its ambition to be Net Zero carbon by 2030. The primary priority for Net Zero Newcastle is to focus on the immediate improvement to air quality that can be achieved by addressing harmful emissions by reducing the dominance of the private car on the city and facilitating a dramatic growth in active travel. The Priority Action T3 refers indirectly to air quality:

“Systematically develop and implement plans to remove private motorized vehicles from the city centre, commercial districts and sensitive part of the city.”

#### Smoke Control Area and Solid Fuel Enforcement Policy

This policy aims to guide residents and businesses on the legal use of solid fuels within Newcastle’s Smoke Control Area (SCA), to reduce air pollution and protect public health by controlling smoke emissions from chimneys, and to clarify enforcement procedures for breaches related to burning solid fuels and selling unauthorised fuels.

Newcastle upon Tyne is entirely designated as a Smoke Control Area under the Clean Air Act 1993. Emitting smoke from a chimney is prohibited unless using authorised fuels or DEFRA-approved appliances. Unauthorised fuels (e.g. wood, coal) can only be used in exempt appliances.

The policy supports cleaner air by reducing emissions of PM10 and PM2.5 which are harmful to health. It reduces risks of respiratory and cardiovascular issues linked to smoke pollution. Residents and businesses are held responsible for compliance, with financial penalties and potential prosecution for breaches, and local fuel suppliers must comply with strict standards, affecting how solid fuels are sold and marketed.

#### Health and Wellbeing Strategy 2023 – 2028

The Health and Wellbeing Strategy is a high-level strategic plan for improving the health and wellbeing of the local population. One of the ambitions is to create healthy and sustainable places and safe communities.

Actions to combat climate change, which benefit all, can improve health and aid recovery from the pandemic, in addition to preserving the planet in a liveable state. The impact of clean air, reducing emissions of greenhouse gases through better transport, food and energy use can result in improved physical and mental health amongst the population. In addition, many of the measures that can be taken to address climate change, through mitigation (reduction) of greenhouse gas emissions and adapting to the impacts of climate change, offer co-benefits for the health and wellbeing of residents. Some examples include improved mental health and wellbeing from a greener and cooler city through targeted urban tree planting programmes, improved air quality and health outcomes by supporting a shift in transport modal share towards active travel and Ultra Low Emission Vehicles, and significant inclusive economic growth from the Net Zero transition.

One of the actions to achieve healthy and sustainable places and safe communities is to

“Actively support measures that deliver clean air and environmental improvements […]”

#### Newcastle Council Plan 2024 – 2027

The Council plan has two simple but fundamental purposes: it sets out the outcome the Council want for their residents and the city, and how the Council will strive to achieve them. It is the foundation for the Council’s entire delivery framework, setting interconnected priority areas to direct and inform core strategies and delivery plans. The three overarching priorities are inclusive economy, anti-poverty and net zero. Furthermore, there are six action areas such as infrastructure. The focus of infrastructure includes:

“Reducing transport emissions for a cleaner, greener Newcastle.”

- Glossary of Terms

| Abbreviation | Description |
| --- | --- |
| AQAP | Air Quality Action Plan - A detailed description of measures, outcomes, achievement dates and implementation methods, showing how the local authority intends to achieve air quality limit values’ |
| AQMA | Air Quality Management Area – An area where air pollutant concentrations exceed / are likely to exceed the relevant air quality objectives. AQMAs are declared for specific pollutants and objectives |
| AQS | Air Quality Strategy |
| ASR | Air quality Annual Status Report |
| CAZ | Clean Air Zone |
| CMS | Continuous ambient Monitoring Sites |
| DEFRA | Department for Environment, Food and Rural Affairs |
| DfT | Department for Transport |
| EFT | Emission Factor Toolkit |
| JAQU | Joint Air Quality Unit |
| LAQM | Local Air Quality Management |
| LEVI | Local Electric Vehicle Fund |
| LSOA | Layer Super Output Areas |
| NECA | North East Combined Authority |
| NO2 | Nitrogen Dioxide |
| NOx | Nitrogen Oxides |
| NTEM | National Trip End Model |
| PM10 | Airborne particulate matter with an aerodynamic diameter of 10µm (micrometres or microns) or less |
| PM2.5 | Airborne particulate matter with an aerodynamic diameter of 2.5µm or less |
| SO2 | Sulphur dioxide |
| TEMPro | Trip End Model Presentation Program |
| ZEBRA | Zero Emission Bus Regional Area |

Environmental equity, air quality, socioeconomic status and respiratory health, 2010

Air quality and social deprivation in the UK: an environmental inequalities analysis, 2006

Public Health England. Estimation of costs to the NHS and social care due to the health impacts of air pollution: summary report, May 2018

Newcastle City Council (2024). Council Plan 2024 – 2027. Available at: https://newcastle.gov.uk/sites/default/files/Finance/20240321_Council-Plan.pdf

Newcastle upon Tyne population change, Census 2021 – ONS

Lower layer Super Output Area population estimates (Accredited official statistics) - Office for National Statistics

https://www.gov.uk/government/publications/air-pollution-applying-all-our-health/air-pollution-applying-all-our-health

Office for Health Improvement & Disparities (2025). Public Health Outcomes Framework – at a glance summary for Newcastle upon Tyne. Available at: https://fingertips.phe.org.uk/static-reports/public-health-outcomes-framework/at-a-glance/E08000021.html?area-name=Newcastle%20upon%20Tyne

DEFRA (2025). Emissions Factor Toolkit v13.1. Available at: https://laqm.defra.gov.uk/air-quality/air-quality-assessment/emissions-factors-toolkit/

DfT (2024). Manual count points for site number 47526. Available at: https://roadtraffic.dft.gov.uk/manualcountpoints/47526

DfT (2023). Trip End Model Presentation Program (TEMPro) download. Available at: https://www.gov.uk/government/publications/tempro-downloads

AECOM/WSP Tyneside Authorities (2021). Local Plan Air Quality Modelling (AQ3) Tyneside Air Quality Feasibility 2017 - 2023

Tyneside CAZ Triage Report (2025). Newcastle City Council

Defra (2025). Local Air Quality Monitoring Technical Guidance 2022, Box 1-1. Available at: UK Regions (exc. London) Technical Guidance | LAQM

Frost, Sullivan (2010). Analysis of the Market for Carsharing in North America

C. Lane (2005). PhillyCarShare: First-year social and mobility impacts of carsharing in Philadelphia, Pennsylvania. Transp. Res. Rec., 158–166

Hoerler et. al. (2021). Carsharing experience fostering sustainable car purchasing? Investigating car size and powertrain choice

CoMoUK (2023.) CoMoUK Annual Car Club Report. Available at: https://cdn.prod.website-files.com/6102564995f71c83fba14d54/6645d8ccf0f74f6e2b38382e_CoMoUK%20Car%2…

Jochem et. al. (2020). Does free-floating carsharing reduce private vehicle ownership? The case of SHARE NOW in European cities, Transportation Research Part A: Policy and Practice, Volume 141, November 2020, Pages 373-395. Available at: https://www.sciencedirect.com/science/article/pii/S0965856420307291

Zapmap (2025). Public charge point utilisation. Available at: Public charge point utilisation - Zapmap

DfT (2025). Integrated National Transport Strategy: a call for ideas. Available at: https://www.gov.uk/government/calls-for-evidence/integrated-national-transport-strategy-a-call-for-ideas

DfT (2025). Integrated National Transport Strategy: a call for ideas. Available at: https://www.gov.uk/government/calls-for-evidence/integrated-national-transport-strategy-a-call-for-ideas/integrated-national-transport-strategy-a-call-for-ideas

DfT and Simon Lightwood MP (2025). Transport Minister kicks off regional tour with communities to shape the future of integrated transport. Available at: https://www.gov.uk/government/news/transport-minister-kicks-off-regional-tour-with-communities-to-shape-the-future-of-integrated-transport

UK Parliament (2025). Joined-up journeys: MPs to investigate how integrated transport can be achieved and measured. Available at: Joined-up journeys: MPs to investigate how integrated transport can be achieved and measured - Committees - UK Parliament

HM Government (2021). Net Zero Strategy: Build Back Greener. Available at: https://assets.publishing.service.gov.uk/media/6194dfa4d3bf7f0555071b1b/net-zero-strategy-beis.pdf

Department for Energy Security and Net Zero, Prime Minister’s Office, 10 Downing Street, Department for Business, Energy & Industrial Strategy, The Rt Hon Lord Alok Sharma KCMG and The Rt Hon Boris Johnson (2020). The ten point plan for a green industrial revolution. Available at: https://www.gov.uk/government/publications/the-ten-point-plan-for-a-green-industrial-revolution

NECA (2025). North East Local Transport Plan: Delivering Green Transport. Available at: https://www.northeast-ca.gov.uk/how-we-work/transport/transport-plan

NECA (2025). The Interim North East Local Growth Plan. Available at: https://www.northeast-ca.gov.uk/local-growth-plan

NECA (2024). Go Ultra Low North East. Available at: https://www.northeast-ca.gov.uk/projects/go-ultra-low-north-east#:~:text=The%20Go%20Ultra%20Low%20North%20East%20programme%20aims,fast%20charging%20facilities%20across%20the%20region.%20Portfolio%3A%20Transport

NECA (2023). North East Active Travel Strategy. Available at: https://www.northeast-ca.gov.uk/how-we-work/transport/active-travel-strategy

NECA (2022). Making the Right Travel Choice. Available at: https://www.northeast-ca.gov.uk/how-we-work/transport/making-the-right-travel-choice

NECA (2023). Bus Service Improvement Plan. Available at: https://www.northeast-ca.gov.uk/how-we-work/transport/bus-service-improvement-plan

NECA (2023). North East Zero Emission Vehicle (ZEV) Strategy. Available at: https://www.northeast-ca.gov.uk/how-we-work/transport/zero-emission-vehicle-strategy

NECA (n.d.). North East Rail and Metro Strategy. Available at: https://www.northeast-ca.gov.uk/how-we-work/transport/rail-and-metro-strategy

Newcastle City Council (n.d). Newcastle Local Plan. Available at:  https://newcastle.gov.uk/newcastleplan#DAP

Newcastle City Council (n.d). Movement Strategy. Available at: https://new.newcastle.gov.uk/travel/improvements/movement

Newcastle City Council (2022). Newcastle Green Infrastructure Strategy: Main Report (Part 2 of 3). Available at: https://newcastle.gov.uk/sites/default/files/planning/GI/Part%202%20Main%20Report%20FINALv2%20(1).pdf

Newcastle City Council (2020). Net Zero Newcastle – 2030 Action Plan. Available at: https://new.newcastle.gov.uk/climate-change-and-net-zero/our-mission/net-zero-newcastle-2030-action-plan

Newcastle City Council (2023). Smoke Control Area and Solid Fuel Enforcement Policy. Available at: https://newcastle.gov.uk/sites/default/files/Smoke%20Control%20Area%20and%20Solid%20Fuel%20Enforcement%20Policy_0.pdf

Newcastle City Council (2023). Health and Wellbeing Strategy 2023 – 2028. Available at: https://www.newcastle.gov.uk/sites/default/files/HEALTH%20AND%20WELLBEING%20STRATEGY%20FINAL%20MARCH%202023.pdf

Newcaslte City Council (2024). Council Plan 2024 – 2027. Available at: https://newcastle.gov.uk/sites/default/files/Finance/20240321_Council-Plan.pdf